## Feuille1
Task	Type	Priority	Effort	Where	Status
Add a README on GitHub	Doc	High	Small	All	Ok
Create vignettes to demonstrate package functioning and see how user-friendly functions are	Code	High	Mid	All
Check and improve documentation for existing functions	Code	High	High	All	Ok
Create Rmd to export analyses with shinyMeta	Interface	High	High	All
Remove select species to exclude	Interface	High	Small	All species	Ok
Code to compute diversity per camera	Code	High	Mid	All species
Plot diversity per camera	Code	High	Mid	All species
Add facetting columns in interface for plot bars	Code	High	Mid	All species
Correct bug → show cameras for mica data	Interface	High	Small	Import	Ok
Change clean_data arguments: remove mapping and replace it with cast types directly named as the columns. Also adapt interface, tests and vignettes.	Interface + code	High	Mid	Import	Ok
Create interface for one species	Interface	High	Mid	One species
Code for one species: compute activity times, plot activity times, compute naive occupancy	Code	High	High	One species
Add new module to select data	Interface	High	Small	Select data	Ok
Select data functions → based on species or on cameras	Interface + code	High	Mid	Select data	Ok
Select data functions → based on values of a third column	Interface + code	High	Mid	Select data
Correct trapping nights bug (when camera df provided but no setup or retrieval)	Interface	High	Small	Summary	Ok
Cameras summary: better way to show code	Interface	High	Small	Summary
Plot map : add camera info on map on click: camera ID, start/end, species seen	Code	High	Mid	Summary
Camera activity: add option for setup/retrieval boxes	Code	High	Mid	Summary
Species summary: create function (species, seen on x cameras, RAI, n pics)	Code	High	High	Summary
Remove Two species	Interface	High	Small	Two species	Ok
Select data functions → based on dates	Interface + code	Mid	Mid	Select data
Remove magrittr dependency	Code	Mid	Small	All	Ok
Remove ShinyDashboard and lubridate dependency?	Code	Mid	Small	All
Change package description (This package…)	Code	Mid	Small	All	Ok
Better theme (colors, fonts)	Interface	Mid	Mid	All
Add option to give datasets in input for Shiny	Code	Mid	Mid	All
Change format table arguments (remove mapping and use column names directly in cast_types). Also adapt interface, tests and vignettes.	Interface + code	Mid	Mid	Import	Ok
Remove date format box but create custom date parsing function	Code	Mid	Mid	Import	Ok
Rearrange date time (Radio buttons on the left and date or date time on the right in vertical format)	Interface	Mid	Mid	Import
Move coordinates format below lon/lat	Interface	Mid	Mid	Import	Ok
Add info (?) next to columns	Interface	Mid	High?	Import
Adapt functions arguments: eg for clean_data allow the user to provide dfcam and dfrec, and dfrec can also be a datapackage object that will be handled differently (eg remove data also in metadata).	Code	Mid	High	Import
Update the way of counting cameras	Code	Mid	Small	Summary	Ok
Update species count (take into account only species)	Code	Mid	Small	Summary
Correct activity times to match newly computed times from camera	Interface	Mid	Small	Summary	Ok
Move map and cameras in columns	Interface	Mid	Small	Summary	Ok
Plot map: create warning if camera not shown	Interface	Mid	Small	Summary
Camera activity: warning if camera not shown	Interface	Mid	Small	Summary
Camera activity: add option for custom colors	Code	Mid	Mid	Summary
Camera activity: add option for axis ticks width and date formatting	Code	Mid	Mid	Summary
Cameras summary: add nb of species seen on camera and npic	Code	Mid	Mid	Summary
Add checkbox print name besides camera	Interface	Mid	Mid	Summary
Modify clean_data to remove camera columns after split	Code	Mid	Small	Import
Modify data import to get only 2 components (remove $data layer) and adapt other functions	Code	Mid	Mid	Import
Modify plot_species_bars to allow to plot non-animals too	Code	Mid	Mid	Summary
Split code functions in several files	Code	Small	Small	All	Ok
Rename lat/lon	Interface	Small	Small	Import	Ok
Place cameras before lon lat	Interface	Small	Small	Import	Ok
Add a format argument instead of tryFormats in add_tryformats	Code	Small	Small	Import
More flexible data cleaning functions → add options to filter NA, to reorder etc.	Code	Small	Small	Import
Place lat besides lon and retrieval besides setup	Interface	Small	Mid	Import
Accomodate either date or datetime or date + time in camera setup	Code	Small	High	Import
Automatically choose date + time or datetime on data import	Interface	Small	High	Import
Camera activity: add checkbox to tick show setup/retrieval times or not	Interface	Small	Small	Summary
Plot species bars : add code to take into account non-species