## Feuille1
Task	Type	Priority	Effort	Where	Status
Add option to give datasets in input for Shiny	Code	Mid	Mid	All	Next
Allow to specify specific timezone (now its UTC by default)	Code + interface	High	Mid	All	Next
Make lonlat optional	Code + interface	High	Mid	Import	Ok
Add chart instead of map option for diversity and presence map	Code + interface	High	High	One species + All species	Ok
Add a README on GitHub	Doc	High	Small	All	Ok
Check and improve documentation for existing functions	Code	High	High	All	Ok
Create Rmd to export analyses with shinyMeta	Interface	High	High	All	Ok
Remove magrittr dependency	Code	Mid	Small	All	Ok
Change package description (This package…)	Code	Mid	Small	All	Ok
Split code functions in several files	Code	Small	Small	All	Ok
Remove select species to exclude	Interface	High	Small	Allspecies	Ok
Code to compute diversity per camera	Code	High	Mid	Allspecies	Ok
Plot diversity per camera	Code	High	Mid	Allspecies	Ok
Add radiobutton to choose between count and npic in interface for plot bars	Code	High	Mid	Allspecies	Ok
Plot species bars : add code to take into account non-species	Code	High	Mid	Allspecies	Ok
Add dates filtering in filter data	Code + interface	High	Mid	Filter	Ok
Add plot to previsualize filtered data	Code + interface	Mid	High	Filter	Ok
Correct bug → show cameras for mica data	Interface	High	Small	Import	Ok
Change clean_data arguments: remove mapping and replace it with cast types directly named as the columns. Also adapt interface, tests and vignettes.	Code + interface	High	Mid	Import	Ok
Rename lat/lon	Interface	Low	Small	Import	Ok
Place cameras before lon lat	Interface	Low	Small	Import	Ok
Place lat besides lon and retrieval besides setup	Interface	Low	Mid	Import	Ok
Change format table arguments (remove mapping and use column names directly in cast_types). Also adapt interface, tests and vignettes.	Code + interface	Mid	Mid	Import	Ok
Remove date format box but create custom date parsing function	Code	Mid	Mid	Import	Ok
Move coordinates format below lon/lat	Interface	Mid	Mid	Import	Ok
Rearrange date time (date or date timeside by side)	Interface	Mid	Mid	Import	Ok
Add info (?) next to columns	Interface	Mid	High?	Import	Ok
Modify clean_data to remove camera columns after split	Code	Mid	Small	Import	Ok
Create interface for one species	Interface	High	Mid	One species	Ok
Code for one species: compute activity times	Code	High	High	One species	Ok
Code for one species: plot activity times	Code	High	High	One species	Ok
Check von Mises use (biblio)	Code + biblio	High	Mid	One species	Ok
look into activity package and change code?	Code	High	Small	One species	Ok
replace custom function with fitact	Code	High	Small	One species	Ok
von Mises vignette	Code	High	Mid	One species	Ok
Add new module to select data	Interface	High	Small	Select data	Ok
Select data functions → based on species or on cameras	Code + interface	High	Mid	Select data	Ok
Select data functions → add date filtering	Code + interface	High	High	Select data	Ok
Correct trapping nights bug (when camera df provided but no setup or retrieval)	Interface	High	Small	Summary	Ok
Cameras summary: better way to show code	Interface	High	Small	Summary	Ok
Species summary: create function (species, seen on x cameras, RAI, n pics)	Code	High	High	Summary	Ok
Camera activity plot: add tick for setup/retrieval boxes	Interface	High	Small	Summary	Ok
Add checkbox to choose to display camera names on map	Interface	Low	Mid	Summary	Ok
Camera activity plot: add option for setup/retrieval boxes	Code	Low	Mid	Summary	Ok
Camera activity: add option for axis ticks width and date formatting	Code	Low	Mid	Summary	Ok
Camera activity: add checkbox to tick show setup/retrieval times or not	Interface	Low	Small	Summary	Ok
Update the way of counting cameras	Code	Mid	Small	Summary	Ok
Correct activity times to match newly computed times from camera	Interface	Mid	Small	Summary	Ok
Move map and cameras in columns	Interface	Mid	Small	Summary	Ok
Camera activity: add option for custom colors	Code	Mid	Mid	Summary	Ok
Modify plot_species_bars to allow to plot non-animals too	Code	Mid	Mid	Summary	Ok
Remove Two species	Interface	High	Small	Two species	Ok
add vignette read camtrapDP data	Code	Mid	Small	Import	Ok
Create vignettes to demonstrate package functioning and see how user-friendly functions are	Code	High	Mid	All	Ongoing
Better theme (colors, fonts)	Interface	Mid	Mid	All	Ongoing
Remove ShinyDashboard and lubridate dependency?	Code	Low	Small	All
Merge summarize_species and get_diversity_table functions ? (or at least reuse some parts)	Code	Low	Mid	Allspecies
Handle NA species (in case observation type is not animal) in get diversity table: for now only species is used and not obs type	Code	Mid	Mid	Allspecies
Add indep filter option in first page and add option to use filtered or non-filtered data in the analyses	Code + interface	Low	High	Filter
Add a format argument instead of tryFormats in add_tryformats	Code	Low	Small	Import
More flexible data cleaning functions → add options to filter NA, to reorder etc.	Code	Low	Small	Import
Accomodate either date or datetime or date + time in camera setup	Code	Low	High	Import
Automatically choose date + time or datetime on data import	Interface	Low	High	Import
Adapt functions arguments: eg for clean_data allow the user to provide dfcam and dfrec, and dfrec can also be a datapackage object that will be handled differently (eg remove data also in metadata).	Code	Low	High	Import
Modify data import to get only 2 components (remove $data layer) and adapt other functions	Code	Low	Mid	Import
Code for one species: compute naive occupancy	Code	High	High	One species
Add RAI on presence map	Code + interface	High	Mid	One species	Next
Add option to filter out cameras filtered when removing the species	Code	Low	Mid	Select data
Add validate statements to prevent from using empty tables if no cameras or no species selected (or incompatible cameras/species)	Interface	Mid	Small	Select data
Select data functions → based on values of a second column	Code + interface	High	Mid	Select data
Plot map : add camera info on map on click: camera ID, coord, duration	Code	Mid	Mid	Summary
open popup directly on click for map with red dot	Interface	Mid	Mid	Summary
Cameras summary: add nb of species seen on camera and npic	Code	Low	Mid	Summary
Plot map: create warning if camera not shown	Interface	Mid	Small	Summary
Add options for activity inference in interface (eg confidence interval, plot centered on midnight)	Interface	Mid	Mid	One species
Check diversity table function → could be merged with species summary?	Code	High	Mid	All species	Next